| WPA Events Committee Meeting Minutes | Date: Sunday April 14, 2013 |
| --- | --- |
|  | Time: 11:00am-1:00pm |
|  | Meeting Location: 662 Palisade Avenue, Jersey City, NJ 07307 Association Address: 662 Palisade Avenue, Jersey City, NJ 07307 Phone: (201) 533-9571 |
| Meeting called by: | WPA Events Committee Meeting | Type of meeting: | Event Planning Meeting |
| Facilitator: | Nick Caballero | Minute taker: | Terri Neuner |
| Timekeeper: | Terri Neuner |  |  |
| Attendees: | WPA Events Planning Committee |
| Agenda Items Discussion Topics | Open Discussions | Start Time/ Duration |
| Call to Order Introductions 11:10am Attendees: Nick Caballero – President Mory Thomas – Trustee Terri Neuner – Secretary Katherine Crawford-Gray – Treasurer Wendy Paul – Vice President Beverly Brown – Trustee Bob Beadreau |

- Annual Fundraiser at the Loew’s Theatre

-Online RSVP and Online Ticket Purchase discussion – On website currently

-Invitations – Save the date – Online invite will be complete tonight (Katherine)

-We have 100 paper invitations so we will share with the Loews

-Invites should go to ALL candidates

-Women of Action lists

-Nominees for all awards

-Address labels will be printed.

-Silent auction and raffle items

-Packages can be created- Loew’s has some already

-Madam Claude’s? Avon Beauty Pack, Home Economics

-Award and bio write up for John Gomez

-Write up received from Friends of the Loew’s

-Format, timing and logistics of event – VIP/ General Admission

-Set up to begin Wed night 6pm

-Tables, step and repeat, silent auction, other supplies.

-Set up Thursday May 2nd – 3:00pm

-Red carpet

-Will chilling / Buckets

-Servers arrive

-Loew’s handle tech set up,

-Wine will arrive Thursday chilled

-Easels will be set up with history of building; discussion, green acres board, park maps

-Wine, Bourbon, food pairing

-Technical set up by Loew’s

**Confirm projector/ screen with Loew’s**

-6pm - VIPs to be escorted to stage (50 guest max)

-2 ticket takers + Katherine

-4 Ushers for VIPs (Nick)

-7pm – General entry

-Loew’s credit card set up

-Walk with Loews this week to talk about logistics

11:50am

-Take some time to present and talk about donated wines (30 minutes in)

-Full schedule will be set

-Sign up sheet for **Maintenance in the Park**

-Volunteer sign up – 10 volunteers- Put out on facebook

-Entertainment – Petit Cubanoson, Organist

-Food and wine pairings

-Staffing

-Bourbon

-Wine glasses, table cloth rentals

-(NJCU-food) (Hoboken Vine-wine)

-Step and Repeat (Hoboken Vine, WPA, NJCU, Loew’s) Wendy, Larger logos needed

-Set up and breakdown

-Volunteer parking **Passes to be handed out					12:06pm

- Planting in the Park

Maintenance in the Park/ Learning Garden Clean Up

-April 27th  - 9am to 2pm (Set up at 8am) Rain or shine

-Girl Scouts

-Hudson County Charter School

-NJCU

-WPA Trustees and friends

-Transplant and plant red bud trees

-Sign in: Wristbands, waivers ** Everyone MUST have wrist band and waivers**

-Food/ Beverage: Water, Gatorade, donuts, fruit, Subway sandwiches

-Additional pointed shovels, forks, wheel barrels needed

Goldman Sachs Community Teamworks

-May 31st  - 8:30am to 3:30pm (set up 7:30am)

-20 Volunteers

-Sign in: Wristbands, waivers

-Food/ Beverage – Water, Gatorade, coffee, donuts, fruit, Shoprite sandwiches (more needed)

-Trustee sign up sheet, at least 5 needed

-Budget - Food/ Water $375

-Budget - Supplies $2000

-Tree donations from Union City						12:17pm

Break

WPA Planting in the Park 						12:40pm

-June 1st  - 9am to 3pm (set up at 8am)

-Reach out to schools ** Lisa** Rainbow girls

-Planting in the tri-park and park 4

-Need write up on trees damaged from Sandy

-Food/ Beverage - Water, Gatorade, coffee, donuts, fruit, Shoprite sandwiches (more needed)

-Entertainment – Walter Parks, Larry drummer DJ (tbd)

-Sign in: Wristbands, waivers ** Nick will get more wrist bands**

-Raffle- 50/50

-Hudson County Improvement Authority- Raffle - Rain Barrel, Compost

-Options:

-Yoga, Grilling, Clown, Face Painting, Sidewalk chalk, Rutgers, Bike Workshop

-**Bike workshop**	Bob B will meet with Central Ave bike shop owner to participate.

-Banner – changeable banner needed, See our website for location

***Lisa to contact** Community Partner for info and tables. Need rocks to hold literature***

-No grilling

-Logos needed for Planting and Movies in the Park

-**Nick and Mory to reach out to graphic designers**

-**Mory to talk to chef about wine/food paring and oysters**

-Set up/ take down

Adjournment										   1:24pm

For those who would like to stay, we will be assembling and addressing invitations for the fund raising event.